## Instructions
PROJECT SCHEDULE TEMPLATE INSTRUCTIONS
Purpose | This schedule template is to help you monitor the tasks that need to be completed throughout your project and track how long they take.
Who is responsible | You are responsible to keep an eye on this template and the overall progress of each task. Your professional consultant will be able to assist you with the overall management of the project.
Definition | Start - the date that the task began
Finish - the date that the task was completed
Note | To add rows, right click on row number in far left column and click insert and a row will insert above selected row
The ‘milestones’ noted in the schedule differ from the grant payment milestones and should not be confused.

## Project Schedule Template
Project Schedule Template
Task Name | Start (Date) | Finish (Date)
PLAN
Step 1. Project initiation activities (refer checklist on page 14)
Step 2. Project plan & site analysis activities (refer checklist on page 26)
Step 3. Concept design activities (refer checklist on page 36)
Milestone 1 - Submit Stage 1 grant application
DESIGN
Milestone 2 - OECD invitation to proceed to Stage 2
Step 4. Detailed design activities (refer checklist on page 39)
Step 5. Planning consent activities (refer checklist on page 40)
Milestone 3 – Submit planning application
Step 6. Building quote preparation activities (refer checklist on page 41)
Milestone 4 – Submit building application
Milestone 5 - Submit Stage 2 grant application
BUILD
Milestone 6 - Grant approved
Milestone 7 – Receive all relevant approvals from PlanSA (refer to page 29)
Step 7. Request building quote activities (refer checklist on page 43)
Milestone 8 – Contractor awarded
Milestone 9 – Complete design documentation (builder if D&C, by professional consultant if construct only). Refer link on page 59 for Fact Sheet 9.
Milestone 10 – Construction works begin
Step 8. Construction activities (refer checklist on page 45)
Milestone 11 – Achieved 50% construction
Milestone 12 – Receipt of practical completion
Step 9. Testing & finish construction activities (refer checklist on page 47)
Milestone 13 – Receipt of occupation certificate
Milestone 14 - Education Standards Board approval
Step 10. Post construction activities (refer checklist on page 52)