## Instructions
RISK REGISTER INSTRUCTIONS
Step | Description | Example
1 | Identify risks to your project and write them in the 'Risk Description' | There is a risk that we cannot engage a professional consultant to help us develop a concept design & ROM cost in time to submit a Stage 1 Grant application
2 | Identidy the impact of the risk and write in 'Risk Impact / Consequence' | results in missing out on grant eligibility
3 | Identify the project phase (drop down menu) | Grant Application
4 | Identify risk category (drop down menu) | Resourcing
5 | Make an estimate of likelihood of risk occuring using table on 'Risk Classification Guide' Tab (1-5) | e.g. 40% chance, i.e. 'possible' = rating of 3
6 | Use the Consequences Guidance in the 'Risk Classification Guide' Tab to decide level of consequence (Negligible to Extreme) | Review "resourcing" category the risk that we can't engage a professional consultant results in: Insufficient capacity or capability to deliver and possible significant impact to scope, schedule and cost = rating of 'Moderate' = 3
7 | Use the Risk Level Matrix in the 'Risk Classification Guide' Tab to work out risk level, i.e. Likelihood x Consequence = Risk Rating | #VALUE!
8 | Identify a risk mitigation method - discuss internally, with your professional consultant, and or support partner | Mitigation: Plan to engage professional consultant by week 2 of the grant program with completion of agreement by Week 4
9 | Identify risk owner | NFP ECEC provider
10 | Repeat steps 5, 6, 7 now that mitigation strategy is in place | 1 x 3 = L
11 | Status of risk (drop down menu) | Open
12 | Risk Trend (drop down menu) | New

## Project Risk Register
RISK REGISTER: South Australia’s Early Childhood Sector Flying Start Infrastruture Grant Program
Project name - RISK REGISTER
Revision XX Date updated: XX/XX/XXXX
Risk Number | Risk Description | Risk Impact / Consequence | Delivery Phase | Initial Risk Level (before mitigation) |  |  |  | Risk Management Strategy (accept, mitigate, transfer) | Risk Owner | Current Status (with mitigation) |  |  | Status | Risk Trend
|  |  |  | Category | Likelihood | Consequence | Risk level |  |  | Likelihood | Consequence | Risk level
EXAMPLE BELOW
1 | There is a risk that we cannot engage a professional consultant to help us develop a concept design & ROM cost in time to submit a Stage 1 Grant application | results in missing out on grant eligibility | Grant Application | Resourcing | 3 | 3 | M | Mitigation: Plan to engage by week 2 of the grant program with completion of agreement by Week 4 | NFP ECEC Provider | 1 | 3 | L | Open | New
2
3
4
5
6
7
8
Add rows above this line

## Risk Classification Guide
Risk Level Matrix
Risk |  | Consequence |  |  |  |  | Project Delivery Phases
| Consequence Þ | Negligible | Minor | Moderate | Major | Extreme | Grant Application
Likelihood ß |  | 1 | 2 | 3 | 4 | 5 | Delivery Planning
Almost Certain (>90%) | 5 | Medium | High | High | Critical | Critical | Construction
Likely (>60%) | 4 | Medium | Medium | High | High | Critical | Commissioning
Possible (>40%) | 3 | Low | Medium | Medium | High | High | Operation
Unlikely (>20%) | 2 | Low | Low | Medium | Medium | Medium
Rare (<10%) | 1 | Low | Low | Low | Medium | Medium
Legend
|  | C | Critical Risk – Immediate action required
|  | H | High Risk – Senior management attention need
|  | M | Moderate Risk – Management responsibility must be specified
|  | L | Low Risk – Management by routine procedures
Consequences Guidance
Category | Consequence
Name | Negligible = 1 | Minor = 2 | Moderate = 3 | Major = 4 | Extreme = 5
Scope | Negligible impact to schedule or cost | Minor impact to schedule or cost | Moderate impact to schedule or cost | Any change to Grant funding approved scope | Significant change to Grant funding approved scope
Schedule | No material impact to schedule | Impact that will deplete <10% of remaining schedule float | Impact that will deplete >10% of remaining schedule float | Impact that will deplete >25% of remaining schedule float and/ or impact key milestones | Impact to publically announced milestones
Cost | No material impact to cost | Impact that will deplete <10% of remaining contingency | Impact that will deplete >10% of remaining contingency | Impact that will deplete >25% of remaining contingency | Impact that will require an additional funding
Health and Safety | No treatment required | Near miss and/or first aid only required | Injury requiring medical treatment and lost time | Serious injury, hospital treatment required; Worksafe reputable incident | Death or permanent disability
Service Disruption | Service disruption <2 hours | Service disruption >2 hours | Service disruption >10 hours | Service disruption >20 hours or outside of agreed standards | Service disruption >30 hours or significantly outside of agreed standards
Quality | Individual breach of internal expectation and/or requirements | Greater than one individual breach of internal expectations and / or requirements | Systemic breach of internal expectations and/or requirements | Breach of external expectation; failure to meet ESB criteria | Breach of external expectation that impacts ability to achieve grant funding timeframes, impacts safety or service
Resourcing | Capacity and / or capability shortfall however no material impact to scope, schedule or cost | Capacity and / or capability shortfall with possible minor impact to scope, schedule or cost | Insufficient capacity or capability to deliver and possible significant impact to scope, schedule and cost | Insufficient capacity or capability to deliver in line with approved scope, schedule and cost | Insufficient capacity or capability to deliver in line with approved scope, schedule and cost and personnel wellbeing at risk
Regulations | No regulatory involvement expected | Regulator/external auditor ‘non- conformance’ or request for further explanation | Regulator/ external auditor issues improvement notice, multiple non- conformances, contractual dispute | Regulator issues notices, corrective action order and/or penalties, common law liability | Criminal prosecution
Reputation | Negligible impact | Stakeholders complaint received | Adverse community issues | Adverse local media coverage only | Adverse state-wide media coverage

## Action Plan (hidden)
10. Risk Assessment Action Plan
This Action Plan is optional - Purpose: is for the individual responsible officer to develop in detail who will do what, when and how to achieve the risk/mitigation outcome.
Risk Assessment Name: (Type name and ISPOT reference for the Risk Assessment) |  |  | Signature | Date
Key resources/individuals required for implementing the mitigation: |  |  | Insert Budget Reference (where relevant)
Background: What is the rationale for this mitigation - how will it assist in reducing the risk? Are there any constraints in achieving the mitigation by the completion date? |  |  | How often will this mitigation be reviewed?
Risk/Mitigation | Action Required | Action Officer | Status Update | Completion Date
Clearly describe the mitigation | What are the actions required to implement the mitigation? (if this mitigation relates to an Program/Project/Other Activity insert the ISPOT reference) | Who is accountable/ responsible for the Mitigation? | Provide details on progress towards achieving the mitigation by the completion date. For example achievement of key milestones | Insert the mitigation completion date.